## Calendar Constraints
constraint_id | owner | constraint_type | start_at | end_at | priority | notes | record_version
CAL-001 | Operations | preferred_event_window | 2026-10-17T09:30:00+08:00 | 2026-10-17T17:00:00+08:00 | hard | Preferred event date | calendar-2026-08-26
CAL-002 | Operations | fallback_event_window | 2026-10-24T09:30:00+08:00 | 2026-10-24T17:00:00+08:00 | soft | Fallback date | calendar-2026-08-26
CAL-003 | TICC | venue_hold | 2026-10-17T07:30:00+08:00 | 2026-10-17T18:30:00+08:00 | hard | Hold expires 2026-09-05 | calendar-2026-08-26
CAL-004 | Programme | keynote_availability | 2026-10-17T10:00:00+08:00 | 2026-10-17T11:00:00+08:00 | hard | Keynote unavailable on fallback date | calendar-2026-08-26
CAL-005 | Operations | decision_deadline | 2026-09-04T17:00:00+08:00 | 2026-09-04T17:00:00+08:00 | hard | Plan and budget decision | calendar-2026-08-26
CAL-006 | Learner Experience | accessibility_walkthrough | 2026-09-25T14:00:00+08:00 | 2026-09-25T16:00:00+08:00 | hard | Venue confirmation required first | calendar-2026-08-26
CAL-007 | Programme | rehearsal_window | 2026-10-16T15:00:00+08:00 | 2026-10-16T18:00:00+08:00 | soft | Remote backup acceptable | calendar-2026-08-26
CAL-008 | TICC | teardown_deadline | 2026-10-17T17:00:00+08:00 | 2026-10-17T18:30:00+08:00 | hard | All vendors clear by 18:30 | calendar-2026-08-26